## Dashboard
AI-CTIDS CAPSTONE PROJECT DASHBOARD
Project | AI-Driven Cyber Threat Detection & Intrusion Detection System |  | Project Health |  | Overall Progress
Duration | 29 Jun 2026 - 16 Aug 2026 |  | 🟢 On Track |  | 40%
Team | Munish Ghai ¦ Sarang Sawant ¦ Darshan Kumar Naidu
Methodology | Agile (7 Weeks) |  | Current Week |  | Next Milestone
|  |  | Week 3 |  | M3 - Model Development
Phase | Progress | Upcoming Deliverables |  | Key KPIs
Project Initiation | 100% | ✓ Model Comparison |  | Total Tasks | 140
Data Understanding & EDA | 100% | ✓ Hyperparameter Tuning |  | Milestones | 7
Data Preparation | 100% | ⏳ SHAP Explainability |  | Risks | 3
Feature Engineering | 100% | ⏳ Deployment Architecture |  | Issues | 1
Model Development | 75% | □ Final Report
Explainability | 60% | □ Presentation
Deployment | 20%
Documentation | 10%

## Project Plan
ID | Week | Phase | Story | Task | Classification | Size | Owner | Start | End | Days | Depends On | Notebook | Milestone | Status
NB-W1-01 | 1 | Notebook PoC | NB-S1: Environment & Data Load | Step 1: Environment setup and library imports | Configuration | S | Sarang Sawant | 2026-06-29 | 2026-06-29 | 1 |  | Step 1 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-02 | 1 | Notebook PoC | NB-S1: Environment & Data Load | Step 2: Load and inspect CICIDS2017 dataset | Data collection | M | Munish Ghai | 2026-06-29 | 2026-06-30 | 2 |  | Step 2 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-14 | 1 | Notebook PoC | NB-S3: Data Cleaning | Step 4.1–4.2: Preprocessing strategy + remove missing target labels | Data preparation | M | Sarang Sawant | 2026-06-29 | 2026-06-30 | 2 |  | Steps 4.1-4.2 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-03 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.1: Data quality audit | Data verification | S | Munish Ghai | 2026-07-01 | 2026-07-01 | 1 |  | Step 3.1 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-15 | 1 | Notebook PoC | NB-S3: Data Cleaning | Step 4.3: Target class validation | Data preparation | S | Sarang Sawant | 2026-07-01 | 2026-07-01 | 1 |  | Step 4.3 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-04 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.2: Dataset profiling | Data verification | S | Munish Ghai | 2026-07-02 | 2026-07-02 | 1 |  | Step 3.2 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-05 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.3: Target variable analysis | Data analysis | S | Munish Ghai | 2026-07-02 | 2026-07-02 | 1 |  | Step 3.3 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-16 | 1 | Notebook PoC | NB-S3: Data Cleaning | Step 4.4: Data type standardization | Data preparation | S | Sarang Sawant | 2026-07-02 | 2026-07-02 | 1 |  | Step 4.4 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-17 | 1 | Notebook PoC | NB-S3: Data Cleaning | Step 4.5: Replace infinite values | Data preparation | S | Sarang Sawant | 2026-07-02 | 2026-07-02 | 1 |  | Step 4.5 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-06 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.4: Network traffic class distribution | Data analysis | S | Darshan Naidu | 2026-07-03 | 2026-07-03 | 1 |  | Step 3.4 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-07 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.5: Class percentage distribution | Data analysis | S | Darshan Naidu | 2026-07-03 | 2026-07-03 | 1 |  | Step 3.5 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-18 | 1 | Notebook PoC | NB-S3: Data Cleaning | Step 4.6: Missing value assessment and imputation | Data preparation | M | Sarang Sawant | 2026-07-03 | 2026-07-04 | 2 |  | Step 4.6 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-08 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.6: Missing values visualization | Data verification | S | Munish Ghai | 2026-07-04 | 2026-07-04 | 1 |  | Step 3.6 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-09 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.7: Infinite values visualization | Data verification | S | Munish Ghai | 2026-07-04 | 2026-07-04 | 1 |  | Step 3.7 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-10 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.8: Data quality dashboard | Data verification | M | Munish Ghai | 2026-07-04 | 2026-07-05 | 2 |  | Step 3.8 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-19 | 1 | Notebook PoC | NB-S3: Data Cleaning | Step 4.7: Constant feature analysis and removal | Data preparation | S | Sarang Sawant | 2026-07-04 | 2026-07-04 | 1 |  | Step 4.7 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-20 | 1 | Notebook PoC | NB-S3: Data Cleaning | Step 4.8: Duplicate feature analysis | Data preparation | S | Darshan Naidu | 2026-07-04 | 2026-07-04 | 1 |  | Step 4.8 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-11 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.9: Missing value heatmap | Data verification | S | Darshan Naidu | 2026-07-05 | 2026-07-05 | 1 |  | Step 3.9 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-12 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.10: Data types distribution | Data verification | S | Darshan Naidu | 2026-07-05 | 2026-07-05 | 1 |  | Step 3.10 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-13 | 1 | Notebook PoC | NB-S2: Data Validation | Step 3.11: Data cleaning decision matrix | Data verification | S | Munish Ghai | 2026-07-05 | 2026-07-05 | 1 |  | Step 3.11 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-21 | 1 | Notebook PoC | NB-S3: Data Cleaning | Step 4.9: Negative value assessment | Data preparation | S | Darshan Naidu | 2026-07-05 | 2026-07-05 | 1 |  | Step 4.9 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W1-22 | 1 | Notebook PoC | NB-S3: Data Cleaning | Step 4.10–4.11: Preprocessing summary + dataset integrity validation | Data preparation | M | Sarang Sawant | 2026-07-05 | 2026-07-05 | 1 |  | Steps 4.10-4.11 | M1: Notebook — Data pipeline (Steps 1–4) | Complete
NB-W2-01 | 2 | Notebook PoC | NB-S4: Feature Engineering | Step 5.1: Target label validation | Data preparation | S | Munish Ghai | 2026-07-06 | 2026-07-06 | 1 |  | Step 5.1 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-02 | 2 | Notebook PoC | NB-S4: Feature Engineering | Step 5.2: Feature and target separation | Data preparation | S | Munish Ghai | 2026-07-06 | 2026-07-06 | 1 |  | Step 5.2 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-09 | 2 | Notebook PoC | NB-S6: Model Development | Step 7.1: Model development strategy | Model analysis | S | Darshan Naidu | 2026-07-06 | 2026-07-06 | 1 |  | Step 7.1 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-10 | 2 | Notebook PoC | NB-S6: Model Development | Step 7.2: Baseline model — Dummy Classifier | Model training | S | Darshan Naidu | 2026-07-06 | 2026-07-06 | 1 |  | Step 7.2 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-15 | 2 | Notebook PoC | NB-S7: Deep Learning | Step 8.1–8.2: ANN architecture and training | Model training | L | Sarang Sawant | 2026-07-06 | 2026-07-08 | 3 |  | Steps 8.1-8.2 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-22 | 2 | Notebook PoC | NB-S9: Hyperparameter Tuning | Step 10.1: Hyperparameter optimization strategy | Model training | S | Darshan Naidu | 2026-07-06 | 2026-07-06 | 1 |  | Step 10.1 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-26 | 2 | Notebook PoC | NB-S10: Deployment Simulation | Step 11.1: Model deployment preparation | Serving infrastructure | S | Sarang Sawant | 2026-07-06 | 2026-07-06 | 1 |  | Step 11.1 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-31 | 2 | Notebook PoC | NB-S11: Monitoring (Notebook) | Step 12.1: Model monitoring overview | Monitoring | S | Munish Ghai | 2026-07-06 | 2026-07-06 | 1 |  | Step 12.1 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-03 | 2 | Notebook PoC | NB-S4: Feature Engineering | Step 5.3: Stratified train-validation-test split | Data preparation | M | Munish Ghai | 2026-07-07 | 2026-07-08 | 2 |  | Step 5.3 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-11 | 2 | Notebook PoC | NB-S6: Model Development | Step 7.3: Logistic Regression model | Model training | M | Darshan Naidu | 2026-07-07 | 2026-07-08 | 2 |  | Step 7.3 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-23 | 2 | Notebook PoC | NB-S9: Hyperparameter Tuning | Step 10.2: Randomized hyperparameter search | Model training | L | Darshan Naidu | 2026-07-07 | 2026-07-09 | 3 |  | Step 10.2 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-27 | 2 | Notebook PoC | NB-S10: Deployment Simulation | Step 11.2: Save deployment artifacts | Serving infrastructure | S | Sarang Sawant | 2026-07-07 | 2026-07-07 | 1 |  | Step 11.2 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-28 | 2 | Notebook PoC | NB-S10: Deployment Simulation | Step 11.3: Deployment simulation | Serving infrastructure | M | Sarang Sawant | 2026-07-07 | 2026-07-08 | 2 |  | Step 11.3 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-32 | 2 | Notebook PoC | NB-S11: Monitoring (Notebook) | Step 12.2: Prediction distribution monitoring | Monitoring | S | Munish Ghai | 2026-07-07 | 2026-07-07 | 1 |  | Step 12.2 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-33 | 2 | Notebook PoC | NB-S11: Monitoring (Notebook) | Step 12.3: Model performance monitoring | Monitoring | S | Munish Ghai | 2026-07-07 | 2026-07-07 | 1 |  | Step 12.3 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-04 | 2 | Notebook PoC | NB-S4: Feature Engineering | Step 5.4: Target label encoding | Data preparation | S | Munish Ghai | 2026-07-08 | 2026-07-08 | 1 |  | Step 5.4 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-12 | 2 | Notebook PoC | NB-S6: Model Development | Step 7.4: Decision Tree classifier | Model training | S | Darshan Naidu | 2026-07-08 | 2026-07-08 | 1 |  | Step 7.4 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-34 | 2 | Notebook PoC | NB-S11: Monitoring (Notebook) | Step 12.4: Data drift monitoring | Monitoring | M | Munish Ghai | 2026-07-08 | 2026-07-09 | 2 |  | Step 12.4 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-05 | 2 | Notebook PoC | NB-S4: Feature Engineering | Step 5.5: Feature scaling using StandardScaler | Data preparation | S | Darshan Naidu | 2026-07-09 | 2026-07-09 | 1 |  | Step 5.5 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-06 | 2 | Notebook PoC | NB-S5: Feature Selection | Step 6.1: Feature engineering strategy | Data preparation | S | Darshan Naidu | 2026-07-09 | 2026-07-09 | 1 |  | Step 6.1 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-13 | 2 | Notebook PoC | NB-S6: Model Development | Step 7.5: Random Forest classifier | Model training | M | Darshan Naidu | 2026-07-09 | 2026-07-10 | 2 |  | Step 7.5 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-16 | 2 | Notebook PoC | NB-S7: Deep Learning | Step 8.3–8.4: ANN performance evaluation and learning curves | Model evaluation | M | Sarang Sawant | 2026-07-09 | 2026-07-10 | 2 |  | Steps 8.3-8.4 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-24 | 2 | Notebook PoC | NB-S9: Hyperparameter Tuning | Step 10.3: Best hyperparameters | Model training | S | Darshan Naidu | 2026-07-09 | 2026-07-09 | 1 |  | Step 10.3 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-29 | 2 | Notebook PoC | NB-S10: Deployment Simulation | Step 11.4: Batch inference example | Serving infrastructure | M | Sarang Sawant | 2026-07-09 | 2026-07-10 | 2 |  | Step 11.4 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-07 | 2 | Notebook PoC | NB-S5: Feature Selection | Step 6.2: Correlation analysis | Data preparation | M | Darshan Naidu | 2026-07-10 | 2026-07-11 | 2 |  | Step 6.2 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-14 | 2 | Notebook PoC | NB-S6: Model Development | Step 7.6: XGBoost classifier | Model training | M | Darshan Naidu | 2026-07-10 | 2026-07-11 | 2 |  | Step 7.6 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-25 | 2 | Notebook PoC | NB-S9: Hyperparameter Tuning | Step 10.4–10.5: Tuned model evaluation + optimization summary | Model evaluation | M | Darshan Naidu | 2026-07-10 | 2026-07-11 | 2 |  | Steps 10.4-10.5 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-30 | 2 | Notebook PoC | NB-S10: Deployment Simulation | Step 11.5–11.6: Deployment summary + real-time API simulation | Serving infrastructure | M | Sarang Sawant | 2026-07-10 | 2026-07-11 | 2 |  | Steps 11.5-11.6 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-35 | 2 | Notebook PoC | NB-S11: Monitoring (Notebook) | Step 12.5: Monitoring dashboard | Monitoring | M | Munish Ghai | 2026-07-10 | 2026-07-11 | 2 |  | Step 12.5 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-08 | 2 | Notebook PoC | NB-S5: Feature Selection | Step 6.3: Correlation-based feature selection | Data preparation | M | Darshan Naidu | 2026-07-11 | 2026-07-12 | 2 |  | Step 6.3 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-17 | 2 | Notebook PoC | NB-S8: Explainable AI | Step 9.1: Explainable AI (XAI) overview | Model analysis | S | Darshan Naidu | 2026-07-11 | 2026-07-11 | 1 |  | Step 9.1 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-18 | 2 | Notebook PoC | NB-S8: Explainable AI | Step 9.2: SHAP global explainability | Model analysis | M | Darshan Naidu | 2026-07-11 | 2026-07-12 | 2 |  | Step 9.2 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-36 | 2 | Notebook PoC | NB-S11: Monitoring (Notebook) | Step 12.6: Production readiness summary | Process & metadata | S | Munish Ghai | 2026-07-11 | 2026-07-11 | 1 |  | Step 12.6 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-19 | 2 | Notebook PoC | NB-S8: Explainable AI | Step 9.3: SHAP local prediction explanation | Model analysis | S | Darshan Naidu | 2026-07-12 | 2026-07-12 | 1 |  | Step 9.3 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-20 | 2 | Notebook PoC | NB-S8: Explainable AI | Step 9.4: LIME local explanation | Model analysis | S | Munish Ghai | 2026-07-12 | 2026-07-12 | 1 |  | Step 9.4 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
NB-W2-21 | 2 | Notebook PoC | NB-S8: Explainable AI | Step 9.5: Explainability summary | Model analysis | S | Munish Ghai | 2026-07-12 | 2026-07-12 | 1 |  | Step 9.5 | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | Complete
P3-T01 | 3 | Production MLOps | S1: Platform Scaffold | Repo layout: intrusion_detection/ shared/ data-ingestion/ batch-trainer/ docker-compose.yml | Configuration | S | Sarang Sawant | 2026-07-13 | 2026-07-13 | 1 |  | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T02 | 3 | Production MLOps | S1: Platform Scaffold | Pin requirements.txt (xgboost shap wandb pydantic pandas scikit-learn joblib) | Configuration | XS | Sarang Sawant | 2026-07-14 | 2026-07-14 | 1 | P3-T01 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T03 | 3 | Production MLOps | S1: Platform Scaffold | shared/schemas.py — NetworkFlowEvent and ThreatPredictionEvent Pydantic models (CICIDS2017 fields) | Configuration | M | Sarang Sawant | 2026-07-15 | 2026-07-15 | 1 | P3-T02 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T04 | 3 | Production MLOps | S1: Platform Scaffold | Trello board + team tracker with story dependencies | Process & metadata | XS | Munish Ghai | 2026-07-16 | 2026-07-16 | 1 |  | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T05 | 3 | Production MLOps | S1: Platform Scaffold | Code review: schemas + repo scaffold | Testing & debugging | XS | Darshan Naidu (reviews Sarang) | 2026-07-17 | 2026-07-17 | 1 | P3-T03 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T06 | 3 | Production MLOps | S2: Data Ingestion & Validation | data-ingestion/load.py — load and inspect CICIDS2017 dataset (Notebook Step 2) | Data collection | M | Munish Ghai | 2026-07-18 | 2026-07-18 | 1 | P3-T05 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T07 | 3 | Production MLOps | S2: Data Ingestion & Validation | Data quality audit profiling missing/inf/class distribution dashboards (Notebook Steps 3.1-3.11) | Data verification | L | Munish Ghai | 2026-07-19 | 2026-07-19 | 1 | P3-T06 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T08 | 3 | Production MLOps | S2: Data Ingestion & Validation | Data cleaning decision matrix + quality report artifact | Data verification | S | Munish Ghai | 2026-07-19 | 2026-07-19 | 1 | P3-T07 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T09 | 3 | Production MLOps | S2: Data Ingestion & Validation | Code review: data ingestion and validation | Testing & debugging | XS | Sarang Sawant (reviews Munish) | 2026-07-19 | 2026-07-19 | 1 | P3-T08 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T10 | 3 | Production MLOps | S3: Data Cleaning & Preprocessing | data-ingestion/cleaning.py — missing labels inf imputation constant/duplicate removal (Notebook Steps 4.1-4.11) | Data preparation | L | Sarang Sawant | 2026-07-19 | 2026-07-19 | 1 | P3-T09 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T11 | 3 | Production MLOps | S3: Data Cleaning & Preprocessing | Dataset integrity validation unit tests after cleaning | Testing & debugging | S | Darshan Naidu | 2026-07-19 | 2026-07-19 | 1 | P3-T10 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T12 | 3 | Production MLOps | S3: Data Cleaning & Preprocessing | Code review: cleaning pipeline | Testing & debugging | XS | Munish Ghai (reviews Sarang) | 2026-07-19 | 2026-07-19 | 1 | P3-T11 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T13 | 3 | Production MLOps | S4: Feature Engineering | Stratified train-val-test split + binary label encoding (Notebook Steps 5.1-5.4) | Data preparation | M | Munish Ghai | 2026-07-19 | 2026-07-19 | 1 | P3-T12 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T14 | 3 | Production MLOps | S4: Feature Engineering | Correlation analysis + feature selection + StandardScaler (Notebook Steps 6.2-6.3 5.5) | Data preparation | M | Darshan Naidu | 2026-07-19 | 2026-07-19 | 1 | P3-T12 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T15 | 3 | Production MLOps | S4: Feature Engineering | Persist processed splits to data/processed/ (parquet + feature manifest) | Process & metadata | S | Sarang Sawant | 2026-07-19 | 2026-07-19 | 1 | P3-T13; P3-T14 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T16 | 3 | Production MLOps | S4: Feature Engineering | Code review: feature engineering pipeline | Testing & debugging | XS | Darshan Naidu (reviews Munish/Sarang) | 2026-07-19 | 2026-07-19 | 1 | P3-T15 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T17 | 3 | Production MLOps | S5: Batch Trainer + W&B | W&B project setup + .env.example + team onboarding | Configuration | S | Sarang Sawant | 2026-07-19 | 2026-07-19 | 1 | P3-T02 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T18 | 3 | Production MLOps | S5: Batch Trainer + W&B | Baseline Dummy + Logistic Regression benchmark (Notebook Steps 7.2-7.3) | Model training | M | Darshan Naidu | 2026-07-19 | 2026-07-19 | 1 | P3-T16 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T19 | 3 | Production MLOps | S5: Batch Trainer + W&B | batch-trainer/train.py — XGBoost with class weights (Notebook Step 7.6) | Model training | M | Darshan Naidu | 2026-07-19 | 2026-07-19 | 1 | P3-T18 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T20 | 3 | Production MLOps | S5: Batch Trainer + W&B | Randomized hyperparameter search + tuned model (Notebook Steps 10.1-10.4) logged to W&B | Model training | L | Darshan Naidu | 2026-07-19 | 2026-07-19 | 1 | P3-T19 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T21 | 3 | Production MLOps | S5: Batch Trainer + W&B | Log ROC-AUC recall F1 confusion matrix feature importance to W&B | Model analysis | S | Darshan Naidu | 2026-07-19 | 2026-07-19 | 1 | P3-T20 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T22 | 3 | Production MLOps | S5: Batch Trainer + W&B | batch-trainer/evaluate.py — holdout attack recall ROC-AUC calibration error | Model evaluation | M | Darshan Naidu | 2026-07-19 | 2026-07-19 | 1 | P3-T20 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T23 | 3 | Production MLOps | S5: Batch Trainer + W&B | Serialize model + scaler + metadata.json (feature list W&B run ID metrics) | Process & metadata | S | Sarang Sawant | 2026-07-19 | 2026-07-19 | 1 | P3-T22 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P3-T24 | 3 | Production MLOps | S5: Batch Trainer + W&B | Code review: training evaluate + W&B integration | Testing & debugging | XS | Munish Ghai (reviews Darshn) | 2026-07-19 | 2026-07-19 | 1 | P3-T23 | M1: CICIDS train + W&B | M3: Production — Platform + CICIDS train + W&B | Not Started
P4-T01 | 4 | Production MLOps | S6: HTTP Inference API | inference-api/predictor.py — load XGBoost scaler threat probability + risk tier | Serving infrastructure | M | Darshan Naidu | 2026-07-20 | 2026-07-20 | 1 | P3-T24 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T02 | 4 | Production MLOps | S6: HTTP Inference API | inference-api/main.py — FastAPI POST /predict GET /healthz GET /readyz GET /metrics (Notebook Step 11.6) | Serving infrastructure | L | Sarang Sawant | 2026-07-21 | 2026-07-21 | 1 | P4-T01 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T03 | 4 | Production MLOps | S6: HTTP Inference API | Single + batch network-flow prediction; validate against NetworkFlowEvent schema | Serving infrastructure | M | Sarang Sawant | 2026-07-22 | 2026-07-22 | 1 | P4-T02 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T04 | 4 | Production MLOps | S6: HTTP Inference API | Save deployment artifacts + batch inference module (Notebook Steps 11.1-11.4) | Serving infrastructure | M | Darshan Naidu | 2026-07-23 | 2026-07-23 | 1 | P4-T01 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T05 | 4 | Production MLOps | S6: HTTP Inference API | Dockerfile + docker-compose service wiring for inference-api | Configuration | S | Sarang Sawant | 2026-07-24 | 2026-07-24 | 1 | P4-T03 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T06 | 4 | Production MLOps | S6: HTTP Inference API | Code review: inference-api + deployment artifacts | Testing & debugging | XS | Munish Ghai (reviews Sarang) | 2026-07-25 | 2026-07-25 | 1 | P4-T04; P4-T05 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T07 | 4 | Production MLOps | S7: Kafka Streaming Consumer | Fork streaming-consumer/consumer.py; load model on startup | Serving infrastructure | M | Sarang Sawant | 2026-07-26 | 2026-07-26 | 1 | P3-T24 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T08 | 4 | Production MLOps | S7: Kafka Streaming Consumer | Consume network-flows topic; publish threat-predictions topic (ThreatPredictionEvent) | Serving infrastructure | L | Sarang Sawant | 2026-07-26 | 2026-07-26 | 1 | P4-T07 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T09 | 4 | Production MLOps | S7: Kafka Streaming Consumer | data-ingestion/replay.py --stream mode: replay CICIDS flows to Kafka in real time | Data collection | M | Munish Ghai | 2026-07-26 | 2026-07-26 | 1 | P3-T15 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T10 | 4 | Production MLOps | S7: Kafka Streaming Consumer | E2E test: replay → Kafka → consumer → threat predictions output | Testing & debugging | M | Darshan Naidu | 2026-07-26 | 2026-07-26 | 1 | P4-T08; P4-T09 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T11 | 4 | Production MLOps | S7: Kafka Streaming Consumer | HTTP vs Kafka SOC runbook: latency throughput failure modes for threat alerts | Process & metadata | S | Munish Ghai | 2026-07-26 | 2026-07-26 | 1 | P4-T10; P4-T06 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P4-T12 | 4 | Production MLOps | S7: Kafka Streaming Consumer | Code review: streaming path + runbook | Testing & debugging | XS | Darshan Naidu (reviews Sarang/Munish) | 2026-07-26 | 2026-07-26 | 1 | P4-T11 | M2: HTTP + Kafka threat scoring | M4: Production — HTTP + Kafka + observability start | Not Started
P5-T01 | 5 | Production MLOps | S8: Metrics & Instrumentation | Prometheus metrics in inference-api (request count latency attack-score histogram) | Monitoring | M | Darshan Naidu | 2026-07-27 | 2026-07-27 | 1 | P4-T06 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T02 | 5 | Production MLOps | S8: Metrics & Instrumentation | Prometheus metrics in streaming-consumer (flows scored lag error rate) | Monitoring | M | Darshan Naidu | 2026-07-28 | 2026-07-28 | 1 | P4-T12 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T03 | 5 | Production MLOps | S8: Metrics & Instrumentation | docker-compose: Prometheus + Grafana + Alertmanager services | Configuration | S | Sarang Sawant | 2026-07-29 | 2026-07-29 | 1 | P4-T06 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T04 | 5 | Production MLOps | S8: Metrics & Instrumentation | Code review: Prometheus instrumentation | Testing & debugging | XS | Munish Ghai (reviews Darshn) | 2026-07-30 | 2026-07-30 | 1 | P5-T02 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T05 | 5 | Production MLOps | S9: Drift & Model Monitoring | drift-monitor/monitor.py — PSI/KS on flow features vs training baseline (Notebook Step 12.4) | Monitoring | L | Munish Ghai | 2026-07-31 | 2026-07-31 | 1 | P3-T23 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T06 | 5 | Production MLOps | S9: Drift & Model Monitoring | replay.py --drift-shift: simulate attack distribution shift for alert testing | Data verification | M | Munish Ghai | 2026-08-01 | 2026-08-01 | 1 | P4-T09 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T07 | 5 | Production MLOps | S9: Drift & Model Monitoring | Prediction distribution monitoring (Notebook Step 12.2) | Monitoring | S | Darshan Naidu | 2026-08-02 | 2026-08-02 | 1 | P4-T10 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T08 | 5 | Production MLOps | S9: Drift & Model Monitoring | Model performance monitoring attack recall precision (Notebook Step 12.3) | Monitoring | S | Darshan Naidu | 2026-08-02 | 2026-08-02 | 1 | P5-T07 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T09 | 5 | Production MLOps | S9: Drift & Model Monitoring | Alertmanager rules: drift threshold + attack recall drop alerts | Monitoring | S | Munish Ghai | 2026-08-02 | 2026-08-02 | 1 | P5-T05; P5-T03 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T10 | 5 | Production MLOps | S9: Drift & Model Monitoring | Code review: drift monitor + performance monitors | Testing & debugging | XS | Sarang Sawant (reviews Munish) | 2026-08-02 | 2026-08-02 | 1 | P5-T08; P5-T09 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T11 | 5 | Production MLOps | S10: XAI Grafana & CI/CD | SHAP explainability endpoint/hook for analyst review (Notebook Steps 9.1-9.3) | Model analysis | M | Darshan Naidu | 2026-08-02 | 2026-08-02 | 1 | P4-T01 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T12 | 5 | Production MLOps | S10: XAI Grafana & CI/CD | Grafana dashboards: threat score latency attack-rate drift SHAP summary (Notebook Step 12.5) | Monitoring | L | Munish Ghai | 2026-08-02 | 2026-08-02 | 1 | P5-T04; P5-T10 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T13 | 5 | Production MLOps | S10: XAI Grafana & CI/CD | GitHub Action workflow_dispatch: ingest sample → train XGBoost → evaluate → publish model | Automation | L | Sarang Sawant | 2026-08-02 | 2026-08-02 | 1 | P3-T23 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T14 | 5 | Production MLOps | S10: XAI Grafana & CI/CD | CI quality gates: min attack recall + ROC-AUC; fail if below notebook baseline | Automation | M | Sarang Sawant | 2026-08-02 | 2026-08-02 | 1 | P5-T13 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T15 | 5 | Production MLOps | S10: XAI Grafana & CI/CD | CI publishes model + metadata.json to models/ release artifacts | Process & metadata | S | Sarang Sawant | 2026-08-02 | 2026-08-02 | 1 | P5-T14 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T16 | 5 | Production MLOps | S10: XAI Grafana & CI/CD | Code review: Grafana dashboards + GitHub Action + SHAP hook | Testing & debugging | XS | Darshan Naidu (reviews Sarang/Munish) | 2026-08-02 | 2026-08-02 | 1 | P5-T11; P5-T12; P5-T15 | M3: SOC observability + drift + CI/CD | M5: Production — Drift, CI/CD, integration | Not Started
P5-T17 | 5 | Production MLOps | S11: Integration & Load Testing | docker-compose up one-command startup script + health-check wait | Automation | M | Sarang Sawant | 2026-08-02 | 2026-08-02 | 1 | P5-T16 | M4: Integration hardening | M5: Production — Drift, CI/CD, integration | Not Started
P5-T18 | 5 | Production MLOps | S11: Integration & Load Testing | Integration tests: HTTP predict Kafka E2E drift alert smoke test | Testing & debugging | L | Darshan Naidu | 2026-08-02 | 2026-08-02 | 1 | P5-T17 | M4: Integration hardening | M5: Production — Drift, CI/CD, integration | Not Started
P5-T19 | 5 | Production MLOps | S11: Integration & Load Testing | Load test inference-api (100 RPS); document p50/p95 latency for threat scoring | Resource management | M | Darshan Naidu | 2026-08-02 | 2026-08-02 | 1 | P5-T18 | M4: Integration hardening | M5: Production — Drift, CI/CD, integration | Not Started
P5-T20 | 5 | Production MLOps | S11: Integration & Load Testing | Load test streaming-consumer; document lag under sustained --stream replay | Resource management | M | Sarang Sawant | 2026-08-02 | 2026-08-02 | 1 | P5-T18 | M4: Integration hardening | M5: Production — Drift, CI/CD, integration | Not Started
P5-T21 | 5 | Production MLOps | S11: Integration & Load Testing | Operational runbook: startup model swap rollback drift response | Process & metadata | M | Munish Ghai | 2026-08-02 | 2026-08-02 | 1 | P5-T19; P5-T20 | M4: Integration hardening | M5: Production — Drift, CI/CD, integration | Not Started
P5-T22 | 5 | Production MLOps | S11: Integration & Load Testing | Code review: integration tests + runbook | Testing & debugging | XS | Munish Ghai (reviews Darshn/Sarang) | 2026-08-02 | 2026-08-02 | 1 | P5-T21 | M4: Integration hardening | M5: Production — Drift, CI/CD, integration | Not Started
P6-T01 | 6 | Production MLOps | S13: Final Deliverables & Presentation | Final repo cleanup: lint pinned deps .env.example no secrets | Configuration | S | Sarang Sawant | 2026-08-03 | 2026-08-04 | 2 | P7-T05 | M6: Presentation + submit | M6: Production — Hardening + repo cleanup | Not Started
P6-T02 | 6 | Production MLOps | S13: Final Deliverables & Presentation | E2E demo rehearsal: CICIDS ingest → train W&B → HTTP predict → Kafka stream → drift → alert | Testing & debugging | M | Darshan Naidu | 2026-08-05 | 2026-08-06 | 2 | P6-T01 | M6: Presentation + submit | M6: Production — Hardening + repo cleanup | Not Started
P7-T01 | 7 | Production MLOps | S12: Design Document & Validation | ML Design Document: AI-CTIDS architecture CICIDS pipeline HTTP vs Kafka observability | Process & metadata | L | Munish Ghai | 2026-08-10 | 2026-08-10 | 1 | P5-T22 | M5: Documentation + validation | M7: Documentation, presentation & video submit | Not Started
W7-T01 | 7 | Deliverables | S14: Final Documentation | Compile ML Design Document — AI-CTIDS full architecture | Process & metadata | L | Munish Ghai | 2026-08-10 | 2026-08-12 | 3 |  |  | M7: Documentation, presentation & video submit | Not Started
W7-T05 | 7 | Deliverables | S15: Presentation & Video | Presentation slides — AI-CTIDS pipeline demo narrative | Process & metadata | M | Munish Ghai (lead) | 2026-08-10 | 2026-08-11 | 2 |  |  | M7: Documentation, presentation & video submit | Not Started
P7-T02 | 7 | Production MLOps | S12: Design Document & Validation | System Operation Validation: Grafana W&B SHAP CI drift alert screenshots | Process & metadata | M | Darshan Naidu | 2026-08-11 | 2026-08-11 | 1 | P5-T22 | M5: Documentation + validation | M7: Documentation, presentation & video submit | Not Started
W7-T02 | 7 | Deliverables | S14: Final Documentation | System Operation Validation report with screenshots | Process & metadata | M | Darshan Naidu | 2026-08-11 | 2026-08-13 | 3 | W7-T01 |  | M7: Documentation, presentation & video submit | Not Started
P7-T03 | 7 | Production MLOps | S12: Design Document & Validation | README: quickstart service map env vars CICIDS data layout | Configuration | M | Sarang Sawant | 2026-08-12 | 2026-08-12 | 1 | P5-T22 | M5: Documentation + validation | M7: Documentation, presentation & video submit | Not Started
W7-T03 | 7 | Deliverables | S14: Final Documentation | Final README + CI/CD DAG + runbook consolidation | Configuration | M | Sarang Sawant | 2026-08-12 | 2026-08-13 | 2 | W7-T01 |  | M7: Documentation, presentation & video submit | Not Started
W7-T06 | 7 | Deliverables | S15: Presentation & Video | Slide review and rehearsal | Testing & debugging | S | Sarang + Darshn | 2026-08-12 | 2026-08-12 | 1 | W7-T05 |  | M7: Documentation, presentation & video submit | Not Started
W7-T07 | 7 | Deliverables | S15: Presentation & Video | E2E demo rehearsal — notebook + production stack | Testing & debugging | M | Darshan Naidu | 2026-08-12 | 2026-08-13 | 2 | P6-T02 |  | M7: Documentation, presentation & video submit | Not Started
P7-T04 | 7 | Production MLOps | S12: Design Document & Validation | CI/CD DAG diagram (docs/ci-cd-dag.mmd) train → gate → publish → deploy | Process & metadata | S | Sarang Sawant | 2026-08-13 | 2026-08-13 | 1 | P5-T15 | M5: Documentation + validation | M7: Documentation, presentation & video submit | Not Started
P7-T05 | 7 | Production MLOps | S12: Design Document & Validation | Writing review: design doc + validation report + README (cross-review) | Testing & debugging | S | All three | 2026-08-14 | 2026-08-14 | 1 | P7-T01; P7-T02; P7-T03 | M5: Documentation + validation | M7: Documentation, presentation & video submit | Not Started
W7-T04 | 7 | Deliverables | S14: Final Documentation | Cross-review all documentation deliverables | Testing & debugging | S | All three | 2026-08-14 | 2026-08-14 | 1 | W7-T01; W7-T02; W7-T03 |  | M7: Documentation, presentation & video submit | Not Started
W7-T08 | 7 | Deliverables | S15: Presentation & Video | Record demo video (10–15 min) — Grafana, W&B, SHAP, CI/CD | Process & metadata | L | Sarang (demo) Darshn (narration) | 2026-08-14 | 2026-08-15 | 2 | W7-T06; W7-T07 |  | M7: Documentation, presentation & video submit | Not Started
P7-T06 | 7 | Production MLOps | S13: Final Deliverables & Presentation | Presentation slides: AI-CTIDS pipeline HTTP vs Kafka SHAP monitoring CI/CD | Process & metadata | M | Munish Ghai (lead) | 2026-08-15 | 2026-08-15 | 1 | P7-T05 | M6: Presentation + submit | M7: Documentation, presentation & video submit | Not Started
W7-T09 | 7 | Deliverables | S15: Presentation & Video | Video review + re-record if needed | Testing & debugging | S | Munish Ghai | 2026-08-15 | 2026-08-15 | 1 | W7-T08 |  | M7: Documentation, presentation & video submit | Not Started
P7-T07 | 7 | Production MLOps | S13: Final Deliverables & Presentation | Slide review | Testing & debugging | XS | Sarang Sawant + Darshan Naidu (review Munish) | 2026-08-16 | 2026-08-16 | 1 | P7-T06 | M6: Presentation + submit | M7: Documentation, presentation & video submit | Not Started
P7-T08 | 7 | Production MLOps | S13: Final Deliverables & Presentation | Record demo video: live docker-compose Grafana W&B CI retrain SHAP explanation | Process & metadata | M | Sarang Sawant (demo) Darshan Naidu (narration) | 2026-08-16 | 2026-08-16 | 1 | P6-T02; P7-T07 | M6: Presentation + submit | M7: Documentation, presentation & video submit | Not Started
P7-T09 | 7 | Production MLOps | S13: Final Deliverables & Presentation | Video review + re-record if needed | Testing & debugging | S | Munish Ghai (reviews) | 2026-08-16 | 2026-08-16 | 1 | P7-T08 | M6: Presentation + submit | M7: Documentation, presentation & video submit | Not Started
P7-T10 | 7 | Production MLOps | S13: Final Deliverables & Presentation | Upload deliverables + post final team tracker to Canvas | Process & metadata | XS | Munish Ghai | 2026-08-16 | 2026-08-16 | 1 | P7-T09 | M6: Presentation + submit | M7: Documentation, presentation & video submit | Not Started
P7-T11 | 7 | Production MLOps | S13: Final Deliverables & Presentation | Buffer / fix open blockers | Testing & debugging | M | All (as needed) | 2026-08-16 | 2026-08-16 | 1 | P7-T10 | M6: Presentation + submit | M7: Documentation, presentation & video submit | Not Started
W7-T10 | 7 | Deliverables | S15: Presentation & Video | Upload deliverables + Canvas submission + team tracker | Process & metadata | XS | Munish Ghai | 2026-08-16 | 2026-08-16 | 1 | W7-T09 |  | M7: Documentation, presentation & video submit | Not Started

## Gantt Chart
AI-CTIDS — 7-Week Plan (Notebook W1–2 · Production W3–6 squeezed · Deliverables W7)
29 Jun 2026 – 16 Aug 2026 · Week 1 starts 29 Jun 2026
[8 empty] | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6 | [6 empty] | W7
ID | Wk | Phase | Task | Owner | Start | End | Status | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16
NB-W1-01 | 1 | Notebook PoC | Step 1: Environment setup and library imports | Sarang Sawant | 2026-06-29 | 2026-06-29 | Complete
NB-W1-02 | 1 | Notebook PoC | Step 2: Load and inspect CICIDS2017 dataset | Munish Ghai | 2026-06-29 | 2026-06-30 | Complete
NB-W1-14 | 1 | Notebook PoC | Step 4.1–4.2: Preprocessing strategy + remove miss… | Sarang Sawant | 2026-06-29 | 2026-06-30 | Complete
NB-W1-03 | 1 | Notebook PoC | Step 3.1: Data quality audit | Munish Ghai | 2026-07-01 | 2026-07-01 | Complete
NB-W1-15 | 1 | Notebook PoC | Step 4.3: Target class validation | Sarang Sawant | 2026-07-01 | 2026-07-01 | Complete
NB-W1-04 | 1 | Notebook PoC | Step 3.2: Dataset profiling | Munish Ghai | 2026-07-02 | 2026-07-02 | Complete
NB-W1-05 | 1 | Notebook PoC | Step 3.3: Target variable analysis | Munish Ghai | 2026-07-02 | 2026-07-02 | Complete
NB-W1-16 | 1 | Notebook PoC | Step 4.4: Data type standardization | Sarang Sawant | 2026-07-02 | 2026-07-02 | Complete
NB-W1-17 | 1 | Notebook PoC | Step 4.5: Replace infinite values | Sarang Sawant | 2026-07-02 | 2026-07-02 | Complete
NB-W1-06 | 1 | Notebook PoC | Step 3.4: Network traffic class distribution | Darshan Naidu | 2026-07-03 | 2026-07-03 | Complete
NB-W1-07 | 1 | Notebook PoC | Step 3.5: Class percentage distribution | Darshan Naidu | 2026-07-03 | 2026-07-03 | Complete
NB-W1-18 | 1 | Notebook PoC | Step 4.6: Missing value assessment and imputation | Sarang Sawant | 2026-07-03 | 2026-07-04 | Complete
NB-W1-08 | 1 | Notebook PoC | Step 3.6: Missing values visualization | Munish Ghai | 2026-07-04 | 2026-07-04 | Complete
NB-W1-09 | 1 | Notebook PoC | Step 3.7: Infinite values visualization | Munish Ghai | 2026-07-04 | 2026-07-04 | Complete
NB-W1-10 | 1 | Notebook PoC | Step 3.8: Data quality dashboard | Munish Ghai | 2026-07-04 | 2026-07-05 | Complete
NB-W1-19 | 1 | Notebook PoC | Step 4.7: Constant feature analysis and removal | Sarang Sawant | 2026-07-04 | 2026-07-04 | Complete
NB-W1-20 | 1 | Notebook PoC | Step 4.8: Duplicate feature analysis | Darshan Naidu | 2026-07-04 | 2026-07-04 | Complete
NB-W1-11 | 1 | Notebook PoC | Step 3.9: Missing value heatmap | Darshan Naidu | 2026-07-05 | 2026-07-05 | Complete
NB-W1-12 | 1 | Notebook PoC | Step 3.10: Data types distribution | Darshan Naidu | 2026-07-05 | 2026-07-05 | Complete
NB-W1-13 | 1 | Notebook PoC | Step 3.11: Data cleaning decision matrix | Munish Ghai | 2026-07-05 | 2026-07-05 | Complete
NB-W1-21 | 1 | Notebook PoC | Step 4.9: Negative value assessment | Darshan Naidu | 2026-07-05 | 2026-07-05 | Complete
NB-W1-22 | 1 | Notebook PoC | Step 4.10–4.11: Preprocessing summary + dataset in… | Sarang Sawant | 2026-07-05 | 2026-07-05 | Complete
NB-W2-01 | 2 | Notebook PoC | Step 5.1: Target label validation | Munish Ghai | 2026-07-06 | 2026-07-06 | Complete
NB-W2-02 | 2 | Notebook PoC | Step 5.2: Feature and target separation | Munish Ghai | 2026-07-06 | 2026-07-06 | Complete
NB-W2-09 | 2 | Notebook PoC | Step 7.1: Model development strategy | Darshan Naidu | 2026-07-06 | 2026-07-06 | Complete
NB-W2-10 | 2 | Notebook PoC | Step 7.2: Baseline model — Dummy Classifier | Darshan Naidu | 2026-07-06 | 2026-07-06 | Complete
NB-W2-15 | 2 | Notebook PoC | Step 8.1–8.2: ANN architecture and training | Sarang Sawant | 2026-07-06 | 2026-07-08 | Complete
NB-W2-22 | 2 | Notebook PoC | Step 10.1: Hyperparameter optimization strategy | Darshan Naidu | 2026-07-06 | 2026-07-06 | Complete
NB-W2-26 | 2 | Notebook PoC | Step 11.1: Model deployment preparation | Sarang Sawant | 2026-07-06 | 2026-07-06 | Complete
NB-W2-31 | 2 | Notebook PoC | Step 12.1: Model monitoring overview | Munish Ghai | 2026-07-06 | 2026-07-06 | Complete
NB-W2-03 | 2 | Notebook PoC | Step 5.3: Stratified train-validation-test split | Munish Ghai | 2026-07-07 | 2026-07-08 | Complete
NB-W2-11 | 2 | Notebook PoC | Step 7.3: Logistic Regression model | Darshan Naidu | 2026-07-07 | 2026-07-08 | Complete
NB-W2-23 | 2 | Notebook PoC | Step 10.2: Randomized hyperparameter search | Darshan Naidu | 2026-07-07 | 2026-07-09 | Complete
NB-W2-27 | 2 | Notebook PoC | Step 11.2: Save deployment artifacts | Sarang Sawant | 2026-07-07 | 2026-07-07 | Complete
NB-W2-28 | 2 | Notebook PoC | Step 11.3: Deployment simulation | Sarang Sawant | 2026-07-07 | 2026-07-08 | Complete
NB-W2-32 | 2 | Notebook PoC | Step 12.2: Prediction distribution monitoring | Munish Ghai | 2026-07-07 | 2026-07-07 | Complete
NB-W2-33 | 2 | Notebook PoC | Step 12.3: Model performance monitoring | Munish Ghai | 2026-07-07 | 2026-07-07 | Complete
NB-W2-04 | 2 | Notebook PoC | Step 5.4: Target label encoding | Munish Ghai | 2026-07-08 | 2026-07-08 | Complete
NB-W2-12 | 2 | Notebook PoC | Step 7.4: Decision Tree classifier | Darshan Naidu | 2026-07-08 | 2026-07-08 | Complete
NB-W2-34 | 2 | Notebook PoC | Step 12.4: Data drift monitoring | Munish Ghai | 2026-07-08 | 2026-07-09 | Complete
NB-W2-05 | 2 | Notebook PoC | Step 5.5: Feature scaling using StandardScaler | Darshan Naidu | 2026-07-09 | 2026-07-09 | Complete
NB-W2-06 | 2 | Notebook PoC | Step 6.1: Feature engineering strategy | Darshan Naidu | 2026-07-09 | 2026-07-09 | Complete
NB-W2-13 | 2 | Notebook PoC | Step 7.5: Random Forest classifier | Darshan Naidu | 2026-07-09 | 2026-07-10 | Complete
NB-W2-16 | 2 | Notebook PoC | Step 8.3–8.4: ANN performance evaluation and learn… | Sarang Sawant | 2026-07-09 | 2026-07-10 | Complete
NB-W2-24 | 2 | Notebook PoC | Step 10.3: Best hyperparameters | Darshan Naidu | 2026-07-09 | 2026-07-09 | Complete
NB-W2-29 | 2 | Notebook PoC | Step 11.4: Batch inference example | Sarang Sawant | 2026-07-09 | 2026-07-10 | Complete
NB-W2-07 | 2 | Notebook PoC | Step 6.2: Correlation analysis | Darshan Naidu | 2026-07-10 | 2026-07-11 | Complete
NB-W2-14 | 2 | Notebook PoC | Step 7.6: XGBoost classifier | Darshan Naidu | 2026-07-10 | 2026-07-11 | Complete
NB-W2-25 | 2 | Notebook PoC | Step 10.4–10.5: Tuned model evaluation + optimizat… | Darshan Naidu | 2026-07-10 | 2026-07-11 | Complete
NB-W2-30 | 2 | Notebook PoC | Step 11.5–11.6: Deployment summary + real-time API… | Sarang Sawant | 2026-07-10 | 2026-07-11 | Complete
NB-W2-35 | 2 | Notebook PoC | Step 12.5: Monitoring dashboard | Munish Ghai | 2026-07-10 | 2026-07-11 | Complete
NB-W2-08 | 2 | Notebook PoC | Step 6.3: Correlation-based feature selection | Darshan Naidu | 2026-07-11 | 2026-07-12 | Complete
NB-W2-17 | 2 | Notebook PoC | Step 9.1: Explainable AI (XAI) overview | Darshan Naidu | 2026-07-11 | 2026-07-11 | Complete
NB-W2-18 | 2 | Notebook PoC | Step 9.2: SHAP global explainability | Darshan Naidu | 2026-07-11 | 2026-07-12 | Complete
NB-W2-36 | 2 | Notebook PoC | Step 12.6: Production readiness summary | Munish Ghai | 2026-07-11 | 2026-07-11 | Complete
NB-W2-19 | 2 | Notebook PoC | Step 9.3: SHAP local prediction explanation | Darshan Naidu | 2026-07-12 | 2026-07-12 | Complete
NB-W2-20 | 2 | Notebook PoC | Step 9.4: LIME local explanation | Munish Ghai | 2026-07-12 | 2026-07-12 | Complete
NB-W2-21 | 2 | Notebook PoC | Step 9.5: Explainability summary | Munish Ghai | 2026-07-12 | 2026-07-12 | Complete
P3-T01 | 3 | Production MLOps | Repo layout: intrusion_detection/ shared/ data-ing… | Sarang Sawant | 2026-07-13 | 2026-07-13 | Not Started
P3-T02 | 3 | Production MLOps | Pin requirements.txt (xgboost shap wandb pydantic … | Sarang Sawant | 2026-07-14 | 2026-07-14 | Not Started
P3-T03 | 3 | Production MLOps | shared/schemas.py — NetworkFlowEvent and ThreatPre… | Sarang Sawant | 2026-07-15 | 2026-07-15 | Not Started
P3-T04 | 3 | Production MLOps | Trello board + team tracker with story dependencie… | Munish Ghai | 2026-07-16 | 2026-07-16 | Not Started
P3-T05 | 3 | Production MLOps | Code review: schemas + repo scaffold | Darshan Naidu (reviews Sarang) | 2026-07-17 | 2026-07-17 | Not Started
P3-T06 | 3 | Production MLOps | data-ingestion/load.py — load and inspect CICIDS20… | Munish Ghai | 2026-07-18 | 2026-07-18 | Not Started
P3-T07 | 3 | Production MLOps | Data quality audit profiling missing/inf/class dis… | Munish Ghai | 2026-07-19 | 2026-07-19 | Not Started
P3-T08 | 3 | Production MLOps | Data cleaning decision matrix + quality report art… | Munish Ghai | 2026-07-19 | 2026-07-19 | Not Started
P3-T09 | 3 | Production MLOps | Code review: data ingestion and validation | Sarang Sawant (reviews Munish) | 2026-07-19 | 2026-07-19 | Not Started
P3-T10 | 3 | Production MLOps | data-ingestion/cleaning.py — missing labels inf im… | Sarang Sawant | 2026-07-19 | 2026-07-19 | Not Started
P3-T11 | 3 | Production MLOps | Dataset integrity validation unit tests after clea… | Darshan Naidu | 2026-07-19 | 2026-07-19 | Not Started
P3-T12 | 3 | Production MLOps | Code review: cleaning pipeline | Munish Ghai (reviews Sarang) | 2026-07-19 | 2026-07-19 | Not Started
P3-T13 | 3 | Production MLOps | Stratified train-val-test split + binary label enc… | Munish Ghai | 2026-07-19 | 2026-07-19 | Not Started
P3-T14 | 3 | Production MLOps | Correlation analysis + feature selection + Standar… | Darshan Naidu | 2026-07-19 | 2026-07-19 | Not Started
P3-T15 | 3 | Production MLOps | Persist processed splits to data/processed/ (parqu… | Sarang Sawant | 2026-07-19 | 2026-07-19 | Not Started
P3-T16 | 3 | Production MLOps | Code review: feature engineering pipeline | Darshan Naidu (reviews Munish/Sarang) | 2026-07-19 | 2026-07-19 | Not Started
P3-T17 | 3 | Production MLOps | W&B project setup + .env.example + team onboarding | Sarang Sawant | 2026-07-19 | 2026-07-19 | Not Started
P3-T18 | 3 | Production MLOps | Baseline Dummy + Logistic Regression benchmark (No… | Darshan Naidu | 2026-07-19 | 2026-07-19 | Not Started
P3-T19 | 3 | Production MLOps | batch-trainer/train.py — XGBoost with class weight… | Darshan Naidu | 2026-07-19 | 2026-07-19 | Not Started
P3-T20 | 3 | Production MLOps | Randomized hyperparameter search + tuned model (No… | Darshan Naidu | 2026-07-19 | 2026-07-19 | Not Started
P3-T21 | 3 | Production MLOps | Log ROC-AUC recall F1 confusion matrix feature imp… | Darshan Naidu | 2026-07-19 | 2026-07-19 | Not Started
P3-T22 | 3 | Production MLOps | batch-trainer/evaluate.py — holdout attack recall … | Darshan Naidu | 2026-07-19 | 2026-07-19 | Not Started
P3-T23 | 3 | Production MLOps | Serialize model + scaler + metadata.json (feature … | Sarang Sawant | 2026-07-19 | 2026-07-19 | Not Started
P3-T24 | 3 | Production MLOps | Code review: training evaluate + W&B integration | Munish Ghai (reviews Darshn) | 2026-07-19 | 2026-07-19 | Not Started
P4-T01 | 4 | Production MLOps | inference-api/predictor.py — load XGBoost scaler t… | Darshan Naidu | 2026-07-20 | 2026-07-20 | Not Started
P4-T02 | 4 | Production MLOps | inference-api/main.py — FastAPI POST /predict GET … | Sarang Sawant | 2026-07-21 | 2026-07-21 | Not Started
P4-T03 | 4 | Production MLOps | Single + batch network-flow prediction; validate a… | Sarang Sawant | 2026-07-22 | 2026-07-22 | Not Started
P4-T04 | 4 | Production MLOps | Save deployment artifacts + batch inference module… | Darshan Naidu | 2026-07-23 | 2026-07-23 | Not Started
P4-T05 | 4 | Production MLOps | Dockerfile + docker-compose service wiring for inf… | Sarang Sawant | 2026-07-24 | 2026-07-24 | Not Started
P4-T06 | 4 | Production MLOps | Code review: inference-api + deployment artifacts | Munish Ghai (reviews Sarang) | 2026-07-25 | 2026-07-25 | Not Started
P4-T07 | 4 | Production MLOps | Fork streaming-consumer/consumer.py; load model on… | Sarang Sawant | 2026-07-26 | 2026-07-26 | Not Started
P4-T08 | 4 | Production MLOps | Consume network-flows topic; publish threat-predic… | Sarang Sawant | 2026-07-26 | 2026-07-26 | Not Started
P4-T09 | 4 | Production MLOps | data-ingestion/replay.py --stream mode: replay CIC… | Munish Ghai | 2026-07-26 | 2026-07-26 | Not Started
P4-T10 | 4 | Production MLOps | E2E test: replay → Kafka → consumer → threat predi… | Darshan Naidu | 2026-07-26 | 2026-07-26 | Not Started
P4-T11 | 4 | Production MLOps | HTTP vs Kafka SOC runbook: latency throughput fail… | Munish Ghai | 2026-07-26 | 2026-07-26 | Not Started
P4-T12 | 4 | Production MLOps | Code review: streaming path + runbook | Darshan Naidu (reviews Sarang/Munish) | 2026-07-26 | 2026-07-26 | Not Started
P5-T01 | 5 | Production MLOps | Prometheus metrics in inference-api (request count… | Darshan Naidu | 2026-07-27 | 2026-07-27 | Not Started
P5-T02 | 5 | Production MLOps | Prometheus metrics in streaming-consumer (flows sc… | Darshan Naidu | 2026-07-28 | 2026-07-28 | Not Started
P5-T03 | 5 | Production MLOps | docker-compose: Prometheus + Grafana + Alertmanage… | Sarang Sawant | 2026-07-29 | 2026-07-29 | Not Started
P5-T04 | 5 | Production MLOps | Code review: Prometheus instrumentation | Munish Ghai (reviews Darshn) | 2026-07-30 | 2026-07-30 | Not Started
P5-T05 | 5 | Production MLOps | drift-monitor/monitor.py — PSI/KS on flow features… | Munish Ghai | 2026-07-31 | 2026-07-31 | Not Started
P5-T06 | 5 | Production MLOps | replay.py --drift-shift: simulate attack distribut… | Munish Ghai | 2026-08-01 | 2026-08-01 | Not Started
P5-T07 | 5 | Production MLOps | Prediction distribution monitoring (Notebook Step … | Darshan Naidu | 2026-08-02 | 2026-08-02 | Not Started
P5-T08 | 5 | Production MLOps | Model performance monitoring attack recall precisi… | Darshan Naidu | 2026-08-02 | 2026-08-02 | Not Started
P5-T09 | 5 | Production MLOps | Alertmanager rules: drift threshold + attack recal… | Munish Ghai | 2026-08-02 | 2026-08-02 | Not Started
P5-T10 | 5 | Production MLOps | Code review: drift monitor + performance monitors | Sarang Sawant (reviews Munish) | 2026-08-02 | 2026-08-02 | Not Started
P5-T11 | 5 | Production MLOps | SHAP explainability endpoint/hook for analyst revi… | Darshan Naidu | 2026-08-02 | 2026-08-02 | Not Started
P5-T12 | 5 | Production MLOps | Grafana dashboards: threat score latency attack-ra… | Munish Ghai | 2026-08-02 | 2026-08-02 | Not Started
P5-T13 | 5 | Production MLOps | GitHub Action workflow_dispatch: ingest sample → t… | Sarang Sawant | 2026-08-02 | 2026-08-02 | Not Started
P5-T14 | 5 | Production MLOps | CI quality gates: min attack recall + ROC-AUC; fai… | Sarang Sawant | 2026-08-02 | 2026-08-02 | Not Started
P5-T15 | 5 | Production MLOps | CI publishes model + metadata.json to models/ rele… | Sarang Sawant | 2026-08-02 | 2026-08-02 | Not Started
P5-T16 | 5 | Production MLOps | Code review: Grafana dashboards + GitHub Action + … | Darshan Naidu (reviews Sarang/Munish) | 2026-08-02 | 2026-08-02 | Not Started
P5-T17 | 5 | Production MLOps | docker-compose up one-command startup script + hea… | Sarang Sawant | 2026-08-02 | 2026-08-02 | Not Started
P5-T18 | 5 | Production MLOps | Integration tests: HTTP predict Kafka E2E drift al… | Darshan Naidu | 2026-08-02 | 2026-08-02 | Not Started
P5-T19 | 5 | Production MLOps | Load test inference-api (100 RPS); document p50/p9… | Darshan Naidu | 2026-08-02 | 2026-08-02 | Not Started
P5-T20 | 5 | Production MLOps | Load test streaming-consumer; document lag under s… | Sarang Sawant | 2026-08-02 | 2026-08-02 | Not Started
P5-T21 | 5 | Production MLOps | Operational runbook: startup model swap rollback d… | Munish Ghai | 2026-08-02 | 2026-08-02 | Not Started
P5-T22 | 5 | Production MLOps | Code review: integration tests + runbook | Munish Ghai (reviews Darshn/Sarang) | 2026-08-02 | 2026-08-02 | Not Started
P6-T01 | 6 | Production MLOps | Final repo cleanup: lint pinned deps .env.example … | Sarang Sawant | 2026-08-03 | 2026-08-04 | Not Started
P6-T02 | 6 | Production MLOps | E2E demo rehearsal: CICIDS ingest → train W&B → HT… | Darshan Naidu | 2026-08-05 | 2026-08-06 | Not Started
P7-T01 | 7 | Production MLOps | ML Design Document: AI-CTIDS architecture CICIDS p… | Munish Ghai | 2026-08-10 | 2026-08-10 | Not Started
W7-T01 | 7 | Deliverables | Compile ML Design Document — AI-CTIDS full archite… | Munish Ghai | 2026-08-10 | 2026-08-12 | Not Started
W7-T05 | 7 | Deliverables | Presentation slides — AI-CTIDS pipeline demo narra… | Munish Ghai (lead) | 2026-08-10 | 2026-08-11 | Not Started
P7-T02 | 7 | Production MLOps | System Operation Validation: Grafana W&B SHAP CI d… | Darshan Naidu | 2026-08-11 | 2026-08-11 | Not Started
W7-T02 | 7 | Deliverables | System Operation Validation report with screenshot… | Darshan Naidu | 2026-08-11 | 2026-08-13 | Not Started
P7-T03 | 7 | Production MLOps | README: quickstart service map env vars CICIDS dat… | Sarang Sawant | 2026-08-12 | 2026-08-12 | Not Started
W7-T03 | 7 | Deliverables | Final README + CI/CD DAG + runbook consolidation | Sarang Sawant | 2026-08-12 | 2026-08-13 | Not Started
W7-T06 | 7 | Deliverables | Slide review and rehearsal | Sarang + Darshn | 2026-08-12 | 2026-08-12 | Not Started
W7-T07 | 7 | Deliverables | E2E demo rehearsal — notebook + production stack | Darshan Naidu | 2026-08-12 | 2026-08-13 | Not Started
P7-T04 | 7 | Production MLOps | CI/CD DAG diagram (docs/ci-cd-dag.mmd) train → gat… | Sarang Sawant | 2026-08-13 | 2026-08-13 | Not Started
P7-T05 | 7 | Production MLOps | Writing review: design doc + validation report + R… | All three | 2026-08-14 | 2026-08-14 | Not Started
W7-T04 | 7 | Deliverables | Cross-review all documentation deliverables | All three | 2026-08-14 | 2026-08-14 | Not Started
W7-T08 | 7 | Deliverables | Record demo video (10–15 min) — Grafana, W&B, SHAP… | Sarang (demo) Darshn (narration) | 2026-08-14 | 2026-08-15 | Not Started
P7-T06 | 7 | Production MLOps | Presentation slides: AI-CTIDS pipeline HTTP vs Kaf… | Munish Ghai (lead) | 2026-08-15 | 2026-08-15 | Not Started
W7-T09 | 7 | Deliverables | Video review + re-record if needed | Munish Ghai | 2026-08-15 | 2026-08-15 | Not Started
P7-T07 | 7 | Production MLOps | Slide review | Sarang Sawant + Darshan Naidu (review Munish) | 2026-08-16 | 2026-08-16 | Not Started
P7-T08 | 7 | Production MLOps | Record demo video: live docker-compose Grafana W&B… | Sarang Sawant (demo) Darshan Naidu (narration) | 2026-08-16 | 2026-08-16 | Not Started
P7-T09 | 7 | Production MLOps | Video review + re-record if needed | Munish Ghai (reviews) | 2026-08-16 | 2026-08-16 | Not Started
P7-T10 | 7 | Production MLOps | Upload deliverables + post final team tracker to C… | Munish Ghai | 2026-08-16 | 2026-08-16 | Not Started
P7-T11 | 7 | Production MLOps | Buffer / fix open blockers | All (as needed) | 2026-08-16 | 2026-08-16 | Not Started
W7-T10 | 7 | Deliverables | Upload deliverables + Canvas submission + team tra… | Munish Ghai | 2026-08-16 | 2026-08-16 | Not Started

## Week Summary
Week | Dates | Phase | Milestone | Tasks | Complete | Remaining
1 | 2026-06-29 to 2026-07-05 | Notebook PoC | M1: Notebook — Data pipeline (Steps 1–4) | 22 | 22 | 0
2 | 2026-07-06 to 2026-07-12 | Notebook PoC | M2: Notebook — Models, XAI, deploy & monitor (Steps 5–12) | 36 | 36 | 0
3 | 2026-07-13 to 2026-07-19 | Production MLOps | M3: Production — Platform + CICIDS train + W&B | 24 | 0 | 24
4 | 2026-07-20 to 2026-07-26 | Production MLOps | M4: Production — HTTP + Kafka + observability start | 12 | 0 | 12
5 | 2026-07-27 to 2026-08-02 | Production MLOps | M5: Production — Drift, CI/CD, integration | 22 | 0 | 22
6 | 2026-08-03 to 2026-08-09 | Production MLOps | M6: Production — Hardening + repo cleanup | 2 | 0 | 2
7 | 2026-08-10 to 2026-08-16 | Production MLOps | M7: Documentation, presentation & video submit | 21 | 0 | 21
Milestone | Offset | Duration
W1 | 0 | 7
W2 | 7 | 7
W3 | 14 | 7
W4 | 21 | 7
W5 | 28 | 7
W6 | 35 | 7
W7 | 42 | 7

## Production Squeeze Map
Original 6-Week Plan | New Week | Notes
Old Week 1 — Platform + train + W&B (24 tasks) | New Week 3 | Jul 13–19
Old Week 2 — HTTP + Kafka serving (12 tasks) | New Week 4 | Jul 20–26
Old Week 3 — Observability + drift + CI/CD (16 tasks) | New Week 5 | Jul 27 – Aug 2
Old Week 4 — Integration hardening (6 tasks) | New Week 5 | Combined with W3
Old Week 5 — Documentation (5 tasks) | New Week 7 | Aug 10–16
Old Week 6 — Presentation partial (2 tasks) | New Week 6 | Cleanup + rehearsal
Old Week 6 — Presentation/video (6 tasks) | New Week 7 | Slides + video + Canvas
Notebook Steps 1–4 | Week 1 | PoC Complete — Jun 29 – Jul 5
Notebook Steps 5–12 | Week 2 | PoC Complete — Jul 6–12